## Sponsor Inputs
# | High level ideas / Features
1 | Create Account
2 | View Restaurants
3 | Search Restaurants
4 | View Menu
5 | Add to Cart
6 | Purchase
7 | Restaurant views order
8 | Restaurant marks order as delivered
Notes:
1 | The above points were listed as draft ideas by the project sponsor.
2 | The project sponsor mentioned that he wants to compete against Talabat.
3 | As a sponsor, I am planning to compete against Talabat.
4 | This is a view only file, you can make a copy then edit in the copy.
5 | You can find a tab named Product Backlog Template, please feel free to use it when creating your product backlog.

## Product Backlog Template
# | Epic | User Story | Priority | Ready to be planned | Planned Sprint | Status
1 | Base | As a user, I want to create account so that I can start using the application | High | Yes | 1 | To Do
2 |  | As a user, I want to login so that I can access my account | High | Yes | 1 | To Do
3 |  | As a user, I want to view restaurants so that I can see available restaurants | High | Yes | 1 | To Do
4 |  | As a user, I want to view menu for a selected restaurant so that I can see the available items | High | Yes | 1 | To Do
5 |  | As a user, I want to view menu for a selected restaurant so that I can see items cost | High | Yes | 1 | To Do
6 |  | As a user, I want to save the selected items of the selected restaurant in the cart so that It can facilitate my purchase | High | Yes | 2 | To Do
7 |  | As a restaurant, I want to view customer order so that I can prepare the order | High | Yes | 2 | To Do
8 |  | As an admin, I want to add a restaurant so that I can control restaurants that appear in the application | High | Yes | 2
9 |  | As an admin, I want to remove a restaurant so that I can control restaurants that appear in the application | High | Yes | 2
10 |  | As a restaurant, I want to update a menu so that I can update the items restaurant provided with their cost | High | Yes | 2
11 |  | As a restaurant, I want to add a menu so that I can the items restaurant provided with their cost | High | Yes | 2
12 | Purchase | As a user, I want to know the total price I will pay so that I can see it is fine to me to pay this price | High | Yes | 3 | To Do
13 |  | As a user, I want to select the type of payment so that I can see which type will be suitable to me | Medium | Yes | 3 | To Do
14 |  | As a user, I want to to be supported of cash , credit card and talabat pay type of payments so that I can be supported by different types according to my suitable case | Medium | Yes | 3 | To Do
15 |  | As a user, I want to use a voucher so that I can get a discount on my order | Medium | Yes | 3
16 | Tracking Order | As a user, I want to track order status so that I can order from another restaurant if the order is rejected | Medium | Yes | 4 | To Do
17 |  | As a user, I want to track order status so that I can be aware of the order status and when it will be delivered | Medium | Yes | 4 | To Do
18 |  | As a restaurant, I want to mark order as delivered so that I can finalize this order | Medium | Yes | 4 | To Do
19 |  | As a user, I want to give feedback on restaurant so that I can show what I like and what I dislike | Medium | Yes | 5 | To Do
20 |  | As a user, I want to search for restaurants so that I can facilitate reaching restaurant I want | Medium | Yes | 5 | To Do
21 |  | As a restaurant, I want to view customer order so that I can accept or reject it | Medium | Yes | 5 | To Do